## Slide 1
Inclusive Housing Toolkit #3
Agency Driven Housing Development

## Slide 2
Acknowledgements
This report was produced as part of My Home My Community, a national initiative of the
Canadian Association of Community Living and People First of Canada.
Inclusive Housing Options for People with Developmental Disabilities received funding from
the National Housing Strategy under the NHS Demonstrations Initiative to produce this work.
The views expressed within are solely of the Canadian Association for Community Living, together
with project partners where expressly stated. Canada Mortgage and Housing Corporation (CMHC)
accepts no responsibility for the views expressed within.

## Slide 3
Inclusive Housing Toolkit
What is it?
An overview guide on the pathways to replicating different models of inclusive housing for individuals with developmental disabilities
A reference tool that breaks down the process into digestible pieces, with tips and specific tools, to be be adapted for your unique housing project
Who is it for?
  Organizations, communities, individuals, and families who are interested in kick-starting the development of inclusive housing
Project leaders, managers, and development teams who want to learn from the experiences of other organizations
About the Toolkit
Based on the development journey of the UNITI-Chorus Case Study, this toolkit maps out a path to replicating this inclusive model
The information is organized into three levels:
  Project phases
  Major activities
  Tools and guides

## Slide 4
Introducing the Series
Toolkit 1 Partnership Driven Development | Toolkit 2 Family Driven Development | Toolkit 3 Agency Driven Development
  This is one of three development pathways detailed in this series. Each explores a different model for producing inclusive affordable housing for people with developmental disabilities.
See www.myhomemycommunity.ca to access the full series, including toolkits and case studies, along with other resources to provoke and promote inclusive affordable housing for people with developmental disabilities.

## Slide 5
Model 3 : Developing Housing
About the Model
What to Know Before Choosing the Model
New housing development or regeneration (as demonstrated by UNITI-Chorus) is a potential inclusive housing pathway for organizations that are interested in taking on new roles.
Under this model, the organization leverages their assets to invest in the creation of new housing for the community, including a number of units dedicated to individuals with developmental disabilities. Such a venture might involve partnerships between several organizations to share out the roles of development, ownership, operation, and providing supports.
This pathway to inclusive housing is complex and requires dedicated effort from leadership at every step in the process. While an organization does not need to have all the expertise in place to begin this journey, they must be open to building capacity, seeking knowledge, mitigating risk, and collaborating with professionals.
This model allows the organization to have the most control over the outcome of the housing solution.
While the model allows for personalization of supports, sufficient funding would be required to enable the appropriate level of supports for individuals with greater support needs.
It is advantageous for an organization to already have some equity and/or land, such as existing properties that could be sold or repurposed. Otherwise, it may take some time to amass the necessary resources for developing a building.
It can be challenging to ensure affordability for all residents. A completely affordable rental building may be an ideal option for many communities, but requires hard work, advocacy, and number crunching to make viable.

## Slide 6
Criteria for Success
Alignment
Having shared values, trust, and alignment on the vision across stakeholders is critical for managing risk and delivering a solution that works for everybody.
Get People Excited
Letting people know what you’re doing, with regular updates, helps to gather support and maintain momentum. Strong advocacy, media attention, and creative branding can go a long way in moving the project along.
Detailed Preparation
Adequate preparation is critical. Though the process can be long, consistent engagement and collaborative planning can ensure that solution delivery is a success.
Just Enough Support
Providing the right level of professional support can enable people to create independent lives for themselves, while leveraging interpersonal connections and technology for assistance.
Tips for the Process
Document the entire process in detail!
Keep the needs of people close to heart and let the process be informed by the philosophy behind the vision
Involve and consult with different stakeholders and experts as needed throughout the process
Be open to learning and pivoting along your journey; key moments of creativity, flexibility, and collaboration can lead to great solutions

## Slide 7
Pathway to Creating Housing
Discover
What is the problem we’re trying to solve?
Who are the stakeholders?
What are the needs and preferences of the individuals we serve?
What are we looking for in our approach to the solution?
What is the housing and support model we want to pursue?
What is the vision and concept of our solution?
What do we need to prepare to execute this vision?
What is the outcome that meets the vision?
What are the actionable steps to creating this outcome?
Who do we need to work with?
What are the pieces we need to develop?
What final preparations do we need to make before we deliver the outcome?
How do we manage the transition from the current situation to the new situation?
What do we need to do to maintain and grow the outcome?
Is the outcome meeting the needs of all stakeholders?
What does the future look like?
What have we learned from our experience?
Define
Develop
Deliver
Extend

## Slide 8
Identify a Need for Change
Explore and Research
Consultation
Synthesize
The journey to creating new solutions is often triggered by dissatisfaction with the current state. What are the issues being faced and what are the forces for change? Initial conversations can lead to forming a group dedicated to discussing and pursuing the issue.
Gain inspiration by looking at existing innovative projects and models across Canada and worldwide. Discover background material in research papers, articles, and case studies. Make time to visit places and connect with organizations that have experience. There are also opportunities to attend conferences, workshops, and information sessions (or initiate your own event!).
Hold consultations with a variety of stakeholders to understand their perspectives on housing. Engaging people early in the process is important to gauge interest, gain insights, and gather support. Some of the most promising ideas and leads can emerge from these conversations.
Toward the end of the discovery phase, pull together all the different pieces of information that will help with defining a solution approach.
Phase 1 : Discover
Pathway to
Creating Housing

## Slide 9
Consultation
Tool Discover
Topics for Discussion
Description:
Consultations are used to gather insights from stakeholders, such as individuals with a disability, their families, staff members, community members, and other experts. The goal is to have structured conversations and hear from different perspectives, particularly the individuals and their advocates, on what an ideal home and life would look like. Some of the outcomes might include identifying the needs of individuals and other stakeholders, discussing values and philosophy, and coming up with some initial solution directions.
In action:
Format: The consultation process could include several information-gathering activities, from a survey to in-person focus groups. For focus groups, there could be a combination of separate conversations with particular stakeholder groups and larger group conversations to bring the perspectives together.
Materials: A list of questions
Method: Consultation sessions may be facilitated by project leaders or volunteers. The session could be an open room discussion or include some conversations in smaller groups, with a share at the end. It is important to have a designated note-taker and/or use handouts for participants to record their thoughts on.
What is the concept of “home” for individuals with a disability?
What are the current challenges to finding housing?
How would people like to live?
What do people need to succeed?
What does inclusivity mean for individuals and their families?
What are the guiding principles any solution must meet?
What are the hopes and fears for the process and outcome?

## Slide 10
Synthesis
Description:
To wrap up the discovery phase, synthesis is a step to summarize all the information and key insights gathered into tangible outputs that can be shared and used in later parts of the project. This could be done by the project team and, as an extra step, validated by stakeholders who were involved in the consultation process.
In action:
Format: Synthesis could be done in stages. It might start with a collaborative session where project leaders get together to sift through information, before dividing up tasks.
Method:
  Look at all the materials and notes
  Look for key insights, patterns
  Categorize and prioritize information
  Summarize into guiding document(s)
  Validate with stakeholders
Tool Discover
Sample Outputs
A summary of the problems with the current state and what do people need or want
A mission statement and list of guiding principles: what are the goals and what are the values that guide us?
A definition of “home” and inclusivity
A list of parties who are interested in the project or wish to be involved
Notes: *Could include an example of Brockville/UNITI values, mission statement

## Slide 11
Vision and
Concept
Whether or not there’s a partnership between several organizations, it’s important to have clear organization structure and governance. There should be discussion on the potential roles and assessment of the internal capacity to take them on. Working on board development at an early stage can help with risk management and build trust between board members and the development team.
Governance
Structure
Using the synthesis of insights and guiding principles, begin working on solidifying the project vision. Holding a visioning session that brings together various stakeholders can help with narrowing in on a cohesive vision. Consider hiring a development consultant at this point to prevent early missteps. This consultant can help to outline the roadmap to development and prepare the board and the project leaders.
Feasibility Activities
Work with the development consultant to help set the stage for the development by bringing together the project concept with the wider context. This involves looking into feasibility, viability, and a plan for execution.
Phase 2 : Define
Pathway to
Creating Housing

## Slide 12
Vision and Concept
Tool Define
Description:
Having a vision and concept that can be pursued is a tool to bring the project to life. The vision includes the scope of the project, the design criteria, and ideas of project components. Ideally, this process will involve participation from key stakeholders, as well as project leaders, to “co-design” the vision. A consultant might be brought on at this point to design, facilitate, and summarize the visioning sessions.
In action:
Format: The visioning session could be a more hands-on workshop, with a balance of discussion and activities to help generate ideas for the vision.
Materials: Worksheets, synthesis materials (e.g. summary of needs, guiding principles), reference materials (e.g. best practices, an inclusivity guide)
Method:
  Using materials, brainstorm ideas for the solution
  Refine the concept and identify the design priorities and criteria
Sample Topics
Physical Building: location, number of units, number of bedrooms, unit features, amenity spaces, outdoor spaces, staff space
Tenure and Cost: tenure model (ownership, life lease, rental), proportion of units for individuals with disabilities, affordability levels
Supports and Services: what kinds of supports, roles in the building, partners, community benefits
Inclusivity: making sure the vision and concept aligns with our definition of inclusivity
Notes: *Could we attach the inclusivity tool?

## Slide 13
Governance Structure
Description:
Determining the governance structure is an important component of the project’s early phase, especially where partnerships are involved. It’s important to make sure that the governance structure is sound, legal, and that board members are prepared for the undertaking of development.
Tips:
Engage in board development activities early on, such as board retreats, risk registry exercises (this may be led by the development consultant)
Conduct an internal capacity assessment to evaluate the ability of the organization to take on the project, as well as the capacity of individual members
Get legal advice to make sure the right holding company owns the land; review and revise the holding organization’s by-laws to ensure they are suitable to own and manage an apartment building
For a partnership between multiple organizations, having the same members on those boards helps to ensure alignment
Guide Define
Sample Structure
Housing Corporation
Support Agency
Charity
Board
Building
Donations
Tenants
Rent
Support
Board Members
Board Members
Board Members
Property Management Firm
Notes: Example of UNITI?

## Slide 14
Create a needs assessment
Create a business plan
Create a pro-forma
Determine the first year operating budget (part of the pro forma)
Determine the timeline
Apply for initial funding (e.g. SEED)
Description:
Feasibility activities are tools that help you understand what is feasible for development, while taking the market context into consideration. Aspects of the project vision and concept might have to be revised to make the project feasible. Many of these activities should be led by a development consultant or other professional, with the involvement of the development team.
In Action:
Method: Work with the development consultant to figure out what information is readily available, what needs to be collected, what needs to be put together, and the execution plan for it all.
Tool Define
Feasibility Activities
Feasibility Checklist

## Slide 15
Acquire Land
Design
Work with Municipalities
There can be several approaches to acquiring land, from buying small parcels in an area over time to selling existing properties and using the proceeds to purchase a new piece of land. Repurposing an existing property that is suitable for redevelopment is another potential approach.
A cohesive design should be informed by the collective vision and guided by the core values of the organization. Further consultation may take place with potential residents and other stakeholders to co-design the building, translating the vision into a feasible design drafted by an architect.
Planning approvals may be required for the development of the building. It can be important to bring advocates to council meetings and engage the community so that they understand the value of the project.
Depending on locality, working with local municipalities might also lead to development benefits, such as breaks on development charges, property taxes, and expedited timelines.
Finance
To have a viable project, the project must fit within a realistic budget. Financial resources can come from a mix of grants, funding, fundraising, and loans.
Construction
Once the project is building permit-ready, it is important to determine a procurement strategy. A general contractor can manage the construction of the building and tendering for the work on trades.
Phase 3 : Develop – Construction
Pathway to
Creating Housing
Once a site has been determined, it is important to hire a number of professionals to move the development process forward. This could include architects, engineers, appraisers, planners, and other development professionals. A development consultant can help you determine which exact professionals are required and when.
Engage Professionals

## Slide 16
Acquire Land
Description:
Acquiring land is key to moving the project from an idea to reality. The type of property may impact the vision and it is important to carefully evaluate the suitability of a site. This process may involve different types of professionals, from legal experts to engineers.
Tips:
Look for surplus municipal and provincial lands (there may be RFP opportunities; discuss with your development consultant and connections in the planning department)
Conduct site due diligence (e.g. check the site for contamination, review planning and conduct an appraisal)
Guide Develop
Is the site accessible for transportation?
Is the site located within a complete community with proximity to services (such as shops and support agencies) and potential for social connections/inclusivity?
Is the site close to where individuals access their current programs and/or work?
Is the site in good condition (e.g. topography, environmental, soil conditions)?
What municipal approvals are required and are there any challenges anticipated in obtaining these approvals?
Site Selection Criteria

## Slide 17
Design
Description:
This step brings together the vision with the feasibility constraints into a final design. This process involves the project team, stakeholders, and other professionals, such as an architect, which the development consultant may help select. Ideally, the process is collaborative and iterative, with opportunities for stakeholder input and feedback. In particular, having resident input on the design can lead to a more inclusive outcome.
In action:
Format: Host a co-design session with the project team, stakeholder representatives, and architect.
Materials: Visioning summary, an initial sketch prepared by the architect or other visual materials
Method:
  Begin with presentation of vision and principles, including ideas, concepts, and constraints
  Facilitate feedback and discussion (this could be incorporated into a hands-on activity)
  Discuss trade-offs and priorities to help the architect refine the design
Tool Develop
Functional planning and layout
Dispersion of units for people with developmental disabilities
Quality/durability of appliances and finishes
Amenities, common spaces and social connection points
Building aesthetics and presence of green space
Proximity to services (or designing for mixed-use)
Cost and affordability
Sustainability and energy efficiency
Accessibility, health and safety
Visitability (for guests)
Parking and transportation
Additional Design Considerations

## Slide 18
Finance
Description:
It is important to consider both the capital costs, soft costs, and operating revenue and expenses when determining the required financing. The development consultant should help to identify sources of funding and put together funding applications.
Tips:
Apply to municipal, provincial, and national programs for affordable housing grants (current programs include the National Housing Strategy Co-Investment Fund, Rental Construction Fund, and Innovation Fund)
Evaluate different financing options for low interest loans with loan insurance
Work together with your local municipality to explore exemptions from development charges, parking requirements and property taxes
Guide Develop
Incoming vs. Outgoing $
grants
fundraising
mortgage
capital costs
(e.g. construction)
soft costs
(e.g. consultant fees)
in
out
operating revenue
operating costs
mortgage payments
Development
Operations
Notes: UNITI-Chorus comparison of financing template

## Slide 19
Construction
Description:
When the project is construction ready, it is time to hire a general contractor who will manage the actual construction of the building, including putting out tenders and hiring construction workers. The development consultant can assist in finding the right general contractor and putting together a construction contract.
Tips:
There are different construction contract types that could be considered. Work together with the development consultant to determine which one is best for the organization.
There could be employment opportunities for individuals with disabilities during construction, in partnership with the contractor.
Construction Contract Types
A design-bid-build, or stipulated price contract (CCDC2)*, is an approach where a fixed price is agreed on for which the general contractor will build the building. This lowers the risk to your organization as, aside for a contingency for inconsistencies in the drawings and calculations etc., there won’t be any additional costs.
Other typical approaches that could be considered are:
  Design-built (CCDC 14)
  Construction management (CCDC 5A/5B).
*CCDC stands for Canadian Construction Documents Committee.
For more information on each of these contract types visit: https://www.ccdc.org/documents/
Guide Develop

## Slide 20
Select Individuals
Support Model
Person-Centred Planning
From the beginning of the project, there might be a large number of interested individuals and families. It is important to have early interviews and planning meetings to identify who might be a good fit, as well as the types of units they would need.
The support model should be designed in collaboration with individuals, families, and support staff to figure out how individuals can be best supported. Having multi-stakeholder sessions to explore needs, concerns, ideas, and roles can help to determine what the model could look like.
As potential tenants are identified, a person-centred planning process is a key preparation tool to plan for independent living. It’s important for individuals, families, and their support networks to think through possible scenarios and create plans for how the individual may live the life they want, while getting the appropriate supports they need.
Ensure
Affordability
Ensuring long-term affordability for individuals maintains stability of tenure. The cost of housing should be affordable, as determined by the person’s income. This might include personal funding, additional housing supplements, subsidies for the building, employment income, and family contributions.
Pathway to
Creating Housing
Phase 3 : Develop – Tenant Selection

## Slide 21
Select Individuals
Description:
As construction is going on, begin the tenant selection process by talking to individuals and their families, starting from the list of interested parties and those who have been involved throughout the development process. Careful screening and preparation is critical for successful tenancy. If the interest surpasses the number of available homes, there should be a system to prioritize individuals for moving to their own home.
Tips:
Create a planning team that is dedicated to working with individuals and families; this could include familiar faces, such as support and program staff
Have an information session for interested families
Conduct one-on-one interviews to identify the needs of the individual and the type of unit they’re interested in
Give out homework; have potential tenants start the person-centred planning process (see Person-Centred Planning)
Evaluate candidates and have selected parties give a written expression of interest
Guide Develop
Level of urgency (e.g. aging parents, poor current living situation, deinstitutionalization)
Commitment from individual and circle of support to do the planning
Ability to afford housing and living expenses
Readiness to move
Interest in moving
Sample Selection Priority Criteria
Notes: UNITI-Chorus priority template

## Slide 22
Person-Centred Planning
Description:
Person-centred planning is a way to prepare and plan for independent living. It uses processes, methods, and tools to understand what is important to a person in their everyday life and what others can do to understand and support them. This process can help to empower individuals, while thinking about risks and how to mitigate them. This tool is adapted from the Semiahoo House Society’s person-centred practices, which includes materials developed by the Learning Community for Person Centred Practices.
Tool Develop
In action:
Format: Person-centred planning can involve a combination of group sessions, one-on-ones, and conversations between the individual and their family or circle.
Method:
  Part one: Exploring how an individual wants to live their life and how they want/need to be supported (see Person-Centred Planning Part 1 attachment)
  Part two: Thinking about what the future might look like (see Person-Centred Planning Part 2 attachment)
  Part three: Planning for independent living (see Person-Centred Planning Part 3 attachment)
Notes: The chorus planning process – the story + attachments

## Slide 23
Support Model
Description:
Developing a support model should be a collaborative effort that brings together the project team and support staff, driven by input from the future tenants and their families. “Just enough support” is a model that aims to increase people’s confidence and abilities, while expanding their network of natural, relationship-based supports. The model should support personalized plans around individuals’ needs.
In action:
Format: A workshop session with different stakeholders can be an effective way to collaborate on the support model concept.
Method:
  Map the support system – how paid workers, families, neighbours, community members, assistive technology work together
  Consider the who, what, when, where, why, and how for support delivery.
  Create a plan including schedules, types of supports, procedures for the building, and communication protocols.
Tool Develop
Consider different support models for different individuals: universal contract (with the main agency), individualized contract (with a self-paid agency), or homeshare
Take care to hire staff who believe in the values behind the model, and work with them to make sure they are comfortable with their role and the risks
Overnight emergency may be provided by a staff member that lives in or close to the building, or an individual’s support network
Tips
Notes: UNITI Chorus natural supports sheet, hiring guidelines, world cafe questions related to support

## Slide 24
There could be a combination of regular rental and long-term rental or life-leases available, depending on the interests of people and the financial requirements for the project. Having a plain language version of the lease is a best practice. The lease should also stipulate that the principal occupant of the unit should be a person with a disability.
The goal of the person-centred planning planning process is to get the individual and their network of support to work on a plan for independent living ahead of their move. As move-in nears, it’s about making the final preparations and making sure support plans are updated and in place.
Moving in can be both exciting and daunting for residents. Allowing residents with disabilities to move in ahead of other tenants can help people to become familiar with the environment, other people, and supports. This transition period also helps staff to become comfortable with procedures and the needs of individual tenants.
Strategies to encourage inclusivity include tours for the community ahead of the building opening, holding events for people in the building to meet each other, and making the common spaces accessible for people to use and share. The option for other residents to receive some education about disabilities might help them be more aware of how to support their neighbours.
Assign Units
Sign
Agreements
As the construction nears completion, families and individuals should be invited to tour the building and choose their own apartment. It could be beneficial for individuals with disabilities to have first choice over the other tenants in the building. The units should be dispersed throughout the building, while maintaining pathways for accessing support. Other units should be made available to the public or assigned through other non-profit agencies.
Preparation for Move-in
Move-in
Foster
Inclusivity
Phase 4 : Deliver
Pathway to
Creating Housing

## Slide 25
Preparation for Move-in
Description:
A move-in plan and checklist is a helpful tool to bring together all the components of the person-centred planning process in preparation for independent living. This would be used by the individual and their family to make sure they are on track in the months leading up to move-in. Project leaders and support workers may lend some guidance or assistance on some of the preparation tasks.
In action:
Materials: A place to store all the planning information and materials (e.g. a folder in a shared drive)
Method:
  Individuals and families create a list of things to do before moving in (with guidance from the planning team)
  Identify things that need to be worked on and reach out for support if needed
Tool Deliver
Update the person-centred plans and information.
Create a plan/list for moving (e.g. buying furniture, packing).
Support the individual to take on more chores in the home (cleaning/cooking etc.).
Give responsibility and encourage individuals to stay home alone for a weekend.
Discuss apartment etiquette and rules.
Discuss issues such as health and safety.
Visit the new neighbourhood and start forming community connections.
Sample Checklist

## Slide 26
Foster Inclusivity
Description:
Creating an inclusivity guide for residents in the building without a disability can help them feel more comfortable about interactions with neighbours, learn how to best handle the presence of support staff, and enable them to be more involved in individuals’ support networks if they wish to be. Tools for these residents should balance education with privacy. The intent is not to single out residents with a disability but provide opportunities for other residents to ask questions and learn.
In action:
Format: Information may be passed on to tenants during their interview or there could be learning sessions as part of other social events in the building
Method: Project leaders may discuss internally, along with individuals and their families, about what is important for other residents to know and what is not. Then, come up with ways to share that information: from formal materials like pamphlets and posters to informal channels, such as a potluck event, where people may be able to have these conversations organically with family and supporters present.
Tool Deliver
Myth-busting around disability
What to do if a tenant with a disability comes to them for an emergency
If people have certain sensitivities or dietary restrictions (for potlucks) – this can be shared informally by individuals and their families at a community event
Examples of Information to Share

## Slide 27
As ongoing work, the organization may have a team that manages the building, from collecting rent to overseeing maintenance and operation. This could also be outsourced to a property management firm.
Ongoing Work
Independent Living
Reflection and Feedback
It’s important to create opportunities to reflect on learnings and collect feedback from the various stakeholders involved on their experiences.
Although preparation and planning are key, real life can be unpredictable and is continuously evolving. Successful independent living can be achieved through flexibility and creativity from staff, clear lines of communication, the willingness of families to support their loved ones to make independent decisions.
Phase 5 : Extend
Pathway to
Creating Housing

## Slide 28
Independent Living
Description:
Having periodic check-ins with residents, especially within the first year of occupancy, can be a good way to gain insights on the experience of independent living for tenants with a disability. These check-ins can be facilitated by the project leaders or individuals’ supports, with follow-up on any specific issues that need to be addressed.
In Action
Format: Check-ins could be in the form of questionnaires for individuals to fill out, with help from support staff if needed, or through an informal interview, individually or in small groups.
Materials: A list of questions
Tool Deliver
What is going well?
What is not going well?
What could be changed?
Do you have any ideas?
What do you need less or more help with?
What questions do you have?
Sample Questions
Notes: UNITI chorus worksheet

## Slide 29
Reflection and Feedback
Does the solution hold up to the principles and vision?
What was the process like and how can it be improved in the next iteration?
Families and Support Staff
What are some of the accomplishments and challenges?
What does your support role look like now and how do you feel about it?
Description:
A reflection tool can be used to gather feedback from people involved in the development process, from the project team to stakeholders that were part of consultations. This is an opportunity for project leaders to hear and reflect on learnings from the process: what went well and what didn’t? What could we do differently next time?
In action:
Format: Feedback could be collected through questionnaires or a session that brings together different stakeholders for a discussion. The discussion could be facilitated by a member of the project team or an outside party.
Materials: A list of questions, the guiding principles (to evaluate the solution)
Tool Develop
Sample Questions

## Slide 30
To learn more about
Inclusive housing models:
www.myhomemycommunity.ca